A Proposal Submitted to

The California Institute of Technology

Pasadena, CA 91125

Att: Dr. Edward C. Stone

in Reference to the

Advanced Composition Explorer (ACE)

Phase C/D RFP

for the

Magnetometer Instrument (MAG)

Section A

Experiment Implementation Plan

Submitted by the

Bartol Research Institute

University of Delaware

Newark, DE 19716

Norman F. Ness

Experiment Manager and

President of the Bartol Research Institute

June 1993

Section A

Table of Contents

µ1. Functional Description and Requirements	1

1.1. Instrument Functional Requirements	1

1.2. MAG Instrument Description	3

1.2.1. Digital Processing Unit	5

1.2.2. Power Converters and Thermal Control	7

2. Management Plan	7

2.1. Approach	7

2.2. Organization	8

2.3. Key Personnel	8

2.4. Institutional Responsabilies	9

2.5. Work Breakdown Structure and WBS Dictionary	11

UD/BRI Direct Technical Labor (1.3.9.1)	11

UD/BRI Materials, Supplies and Other Direct Charges (1.3.9.2)	13

UD/BRI Equipment Purchases (1.3.9.3)	14

UD/BRI Travel (1.3.9.4)	14

UD/BRI Indirect Costs (1.3.9.5)	14

GSFC Code 692 and 695 Tasks (1.3.9.6)	14

2.6. Contract Deliverables	14

2.7. Key Assumptions	15

2.8. Reviews and Reporting	15

2.9. Cost Control	15

2.10. Contract Management	16

3. Development Plan	17

3.1. Instrument Heritage	17

3.2. Changes/Additions from Heritage	17

3.3. Development	17

3.3.1. New Developments Hardware Tasks	17

3.3.2. Software Development	17

3.3.3. GSE Usage	17

3.3.4. Key Decision Points	17

3.3.5. Part Buy Lead Times	17

3.3.6. Key Facilities	17

3.4. Work Flow Diagram and Schedule	18

3.5. Calibration	18

3.5.1. Methodology and Requirements	18

3.6. Test and Integration	18

3.6.1. Instrument Test Matrix w/Facilities Requirements	18

3.6.2. Test and Integration Flow	19

3.6.3. Constraints	19

3.7. Product Assurance	19

3.8. Configuration Control	19

4. Operations Plan	20

4.1. Instrument Commanding	20

4.2. Data Analysis	20

4.2.1. Data Flow	20

4.2.2. Level 0, Level 1 and Level 2 Processing	20

4.2.3. Science Operations Center Interface	21

4.3. Operational Facilities	21

List of Tables

Table 1	Summary of Instrument Characteristics

Table 2	Telemetry Modes

Table 3	Institutional Responsibilities

Table 4.	Instrument Test Matrix

List of Figures

Fig. 1	Block diagram of the ACE/MAG Magnetic Field Experiment

Fig. 2	Schematic of Standard Fluxgate Operation

Fig. 3a	Fluxgate Noise Performance Graphs

Fig. 3b	Noise Power Spectrum for MAG Prototype Sensor

Fig. 4	Range Switching Scheme

Fig. 5	ACE/MAG Team Organization

Fig. 6	Work Breakdown Structure (WBS)

Fig. 7	Work Flow Diagram and Schedule

Fig. 8	Data Processing Flow

# 1 Functional Description and Requirements

## 2 Instrument Functional Requirements

The ACE Magnetic Field Instrument (MAG) will establish the large-scale structure and fluctuation characteristics of the interplanetary magnetic field (IMF) at 1 AU upstream of Earth as functions of time throughout the mission. This experiment will provide:

1.	near real-time data at nominally 30 vectors/second for NOAA support,

2.	continuous data at 3,5 or 6 vectors/sec. for standard analysis, and

3.	snapshot memory data and Fast Fourier Transform data (FFT) based on 30 vectors/sec. acquired on board, working synchronously with blocks of 512 samples (FFT only) each.

These measurements will be precise (0.025%), accurate (<0.08 nT) and ultra-sensitive (0.008 nT/step). The basic instrument is a twin triaxial fluxgate magnetometer system. Each of two identical sensors is mounted at a distance of 4 meters from the center of the spacecraft on booms that extend past the end of diametrically opposite solar panels. The digital processing unit utilizes a 12-bit A/D converter to easily resolve small amplitude fluctuations of the field, and is microprocessor controlled. It also incorporates a dedicated FFT processor developed around high performance DSP integrated circuits, which produces a 32-channel logarithmic spectrum for each axis, synthesized from a "raw" 256-point linear spectrum. All components of the power spectral matrices corresponding to the 32 estimates are transmitted to the ground once every 80 seconds, providing power and phase information together with the corresponding snapshot memory time series data. As in previous instruments developed at GSFC, high reliability is obtained by the use of fully redundant systems and extremely conservative designs. The intrinsic zero drift of the sensors is expected to be below 0.1 nT over periods of up to 6 months. Electrical "flippers" designed to simulate a 180 degree mechanical rotation of the sensors, will be used to monitor the zero level drift associated with aging of electronic components. The use of advanced statistical techniques for estimating absolute zero levels is also planned. The instruments feature a very wide dynamic range of measurements capability, from ± 4 nT up to ± 65,536 nT per axis in eight discrete ranges; the lowest range will be activated by command only, and the remaining ranges either by command or, most commonly, automatically. The upper range permits end-to-end testing in the Earth's magnetic field without the need for special field cancellation coils or magnetic shields. Table 1 summarizes the principal instrument characteristics.

TABLE 1.

Summary Of Instrument Characteristics

Instrument type:	Twin, triaxial fluxgate magnetometers (boom mounted).

Dynamic ranges (8):	4 nT by command; ±16 nT; ±64 nT; ±256 nT; ±1024 nT; ±4096 nT; ±16,384 nT; ±65,536 nT

Digital Resolution (12-bit):	±0.004 nT; ±0.016 nT; ±0.0625 nT; ±.25 nT; ±1.0 nT; ±4.0 nT; ±16.0 nT

Bandwidth:	15 Hz

Sensor noise level:	< 0.006 nT RMS, 0-10 Hz

Sampling rate:	30 vector samples/s in snapshot memory and 3,5 or 6 vector samples/s standard.

Signal Processing:	FFT Processor, 32 logarithmically spaced channels, 0 to 15 Hz. Full spectral matrices generated every 80 seconds for four time series (Bx, By, Bz, |B|).

FFT Windows/Filters:	Full despin of spin plane components, 10% cosine taper, Hanning window, first difference filter.

FFT Dynamic range:	72 dB, m-Law log-compressed, 13-bit normalized to 7-bit with sign

Sensitivity threshold: 	~0.5 x 10-3 nT/Hz in Range 0.

Snapshot memory capacity:	256 Kbits

Trigger modes (3):	Overall Magnitude Ratio, Directional max.-min. peak to peak change, Spectral increase across frequency band (RMS)

Telemetry Modes:	Three, selectable by command.

Mass:	Sensors (2): 450 g. total
Electronics (redundant): 2100 g. total

Power Consumption:	2.4 watts, electronics - regulated 28 Volts ± 2%
1.0 watts , heaters - unregulated 28 Volts

## 3 MAG Instrument Description

The basic instrumentation selected for the ACE Magnetic Field Investigation (MAG) is a modification of the spare MFI instrument built for the WIND mission. The MFI was itself based on the magnetometers previously developed for the Voyager, ISPM, GIOTTO and Mars Observer missions which represent state-of-the-art instruments with unparalleled performance. The basic configuration of MAG consists of twin, wide range (±0.004 to ±65536 nT) triaxial fluxgate magnetometers mounted remote from the spacecraft body on deployable booms, a 12-bit resolution A/D converter system and a microprocessor controlled data processing and control unit (DPU). Each of two identical sensors (labeled M1 and M2) is mounted at the end of a boom that extends beyond the Solar Panels at a distance of 4 meters from the center of the S/C.

A block diagram of the MAG instrumentation is shown in Figure 1. The advantages of the twin magnetometer approach for weak magnetic field measurements like those associated with the IMF, have been proven over many space missions since their original introduction by N. F. Ness and colleagues (1971).

The twin magnetometer system is supported by the fully redundant DPU which interfaces with the spacecraft data and power systems. The use of full redundancy in the MAG instrument is an important feature that emphasizes the critical nature of the magnetic field measurements for the achievement of the ACE science objectives. It significantly reduces the probability of failures and takes advantage of the inherent redundancy provided by the twin magnetometer configuration. This redundancy includes assigning by command either primary or secondary data stream for the M1 sensor and likewise for the M2 sensor. In addition to the block redundancy provided, each magnetometer system incorporates self-resetting electronic "fuses" which isolate the common subsystems in case of catastrophic problems.

Each sensor assembly consists of an orthogonal triaxial arrangement of ring-core fluxgate sensors plus additional elements required for thermal control. The fluxgate sensors are the latest in a series developed for weak magnetic field measurements by Acuña et. al. (1974) and which have been extensively used in missions like VOYAGER, AMPTE, GIOTTO, Mars Observer, CLUSTER, etc. due to their superior performance and low power consumption. The detailed principles of operation of fluxgate magnetometers are well known and will not be repeated here. It is sufficient to refer to Figure 2 for a simplified description of their operation. (For additional information the reader is referred to Ness, 1970 and Acuña, 1974; 1976 a, b). As shown in figure 2 the fluxgate sensors are driven cyclically to saturation by a 15 KHz signal derived from the DPU master clock. The sensor drive signals are derived from an efficient high energy storage system which is capable of driving the ring core sensors to peak excitations which are more than 100 times the coercive saturation force of the cores. This type of excitation eliminates from consideration many "perming" problems which have been attributed to fluxgate sensors in the past. In the absence of an external magnetic field, the fluxgate sensors are "balanced" and no signal appears at the output terminals. When an external field is applied, the sensor balance is disturbed and a signal containing only even harmonics of the drive frequency appears at the output of the sensors. After amplification and filtering, this signal is applied to a synchronous detector and high gain integrating amplifier which is used to generate a current proportional to the magnitude of the applied field which is fed-back to the sensor to null the effective magnetic field seen by it. The output of a single axis magnetometer is then a voltage proportional to the magnitude, direction and polarity of the ambient magnetic field with respect to the sensor axis orientation. A triaxial magnetometer is thus created when three single axis sensors are arranged in an orthogonal configuration and three sets of signal processing electronics are used to produce three output voltages proportional to the orthogonal components of the ambient magnetic field.

The noise performance of the MAG fluxgate sensors is shown in Figures 3a and 3b. Total RMS noise level over the 0-10 Hz band does not exceed 0.006 nT. This noise level is several orders of magnitude below the lowest recorded levels of IMF fluctuations at 1 AU and is more than adequate to properly detect and identify all magnetic field phenomena of interest to MAG.

The six analog signals generated by each of the two magnetometers are digitized by the 12-bit successive approximation A/D converter. The 12-bit resolution allows the recovery of a very large dynamic range of signals spanning 72 dB. To further increase the measurement dynamic range and to accommodate simplified integration and test requirements during spacecraft testing, the dynamic range of the magnetometers can be changed automatically if the magnitude of the measured signals exceeds or drops below established digital thresholds illustrated in Figure 4. In this fashion, the MAG instrumentation can cover eight orders of magnitude in magnetic field measurement capability, from 0.004 nT to 65536 nT per axis. The operation of the automatic ranging system is controlled by the microprocessor and allowed only at clearly defined times in the telemetry frame to avoid ambiguities in the interpretation of the data. When the digitized output of any magnetometer axis exceeds 7/8's of full scale, the microprocessor generates a command to step up (increase) the magnetometer to the next, less sensitive, range. Conversely, when the output of all axes drops below 1/8th of full scale, the DPU commands the appropriate magnetometer to step down (decrease) to the next most sensitive range. A "guard band" of 1/8th scale is provided to avoid the loss of measurements due to saturation until the range is updated. The decision to increase or decrease dynamic range is made at the basic internal sampling. However, the MAG telemetry allocation is not sufficient to allow the transmission of all the data to the ground and on-board data averaging, compression and decimation must be used to reduce the "raw" rate to an acceptable value. These operations are described in more detail later. The DPU also controls calibration sequences which provide the necessary currents to determine the scale factor of each of the M1 and M2 magnetometer axes for various dynamic ranges as well as the determination of zero offsets by implementing a 180º phase reversal of the signals processed by the magnetometer electronics (electronic "flipping").

### 4 Digital Processing Unit

The DPU, including the analog-to-digital converter, is based on the concept of a "smart system" which performs all required operations: data manipulation and formatting, averaging, compaction and decimation, etc. The basic microprocessor used is a radiation hardened version of the popular 80C86, and a block diagram of the DPU architecture is shown in Figure 1. All core operations performed by the system are carried out under the control of interrupt driven software synchronized to the telemetry system clock, subframe and frame rates. The system design is based on a default executive and processing program which is stored and executes in Read-Only-Memory (ROM). All subsequent operations are carried out from ROM and no commands or memory loads are required to obtain valid data from the instrument after initial turn-on. All default parameter values for the system are stored in tables in ROM which, once mapped into RAM during initialization, can later be modified by commands to update calibrations, alignments, sampling rates, zero levels, etc.

The execution of the executive and auxiliary programs is monitored by hardware and software watchdog timers. The external hardware watchdog timer is normally reset by proper execution of the executive program; in the absence of a reset pulse, the watchdog timer will reset the DPU and restart the default ROM program, reloading all default parameters from ROM.

In addition to the core DPU functions described above, to better enable the study of rapid changes in the ambient magnetic field, the MAG instrumentation includes two additional functional elements designed specifically for this purpose:

·	a 256 Kbit "Snapshot Memory" (SSM) and

·	a Fast Fourier Transform Processor (FFT) implemented around a TI320C10 dedicated digital signal processor and associated memory.

This enables the study of the physics of the fine-scale structure of shock waves, directional discontinuities and boundary structures, as well as the various wave modes and non-coherent fluctuations occurring in the solar wind. The snapshot memory can be programmed to trigger upon the occurrence of one or more of the three classes of conditions:

·	A magnetic field magnitude jump.

·	A directional change (peak to peak).

·	Changes in the characteristics of field fluctuations over time.

When the selected condition is satisfied, the contents of the snapshot memory are "frozen". Under normal conditions, the primary magnetometer data sampled at the highest possible rate (30 samples/sec.) is circulated through the snapshot memory with cyclical overwriting once the memory is full. Thus a maximum of 7282 vectors can be stored in memory. This corresponds to approximately 243 seconds of data. The use of memory pointers in the DPU software allows the recovery of data acquired 121 seconds prior to the occurrence of the trigger (i.e., one-half of the buffer). Thus it is possible to study precursor events in high time resolution.

The FFT processor complements the snapshot memory by providing full spectral estimation capabilities in the frequency range of 0-15 Hz for Primary magnetometer data. The basic FFT engine produces raw spectral estimates of the three components of the field in 256 spectral bands using 512 samples of the ambient magnetic field data (i.e. 17 seconds). In addition, the processor computes the magnitude of the magnetic field vectors in the time series being analyzed, its Fast Fourier Transform and the cross-spectral estimates associated with the three orthogonal components. In order to reduce the effects of the large signals associated with the spacecraft spin, the TI320C10 processor is used to despin the spin plane components of the data prior to the computation of the FFT for these axes. Other functions included in the FFT processor are pre-whitening of input data, windowing (cosine taper and Hanning), and data compression. The latter is required to reduce the volume of raw data produced by the spectral analysis (256, 3x3 spectral matrices plus a 256 element time series) to a manageable size which can be accommodated by the telemetry rate allocated to MAG. In the frequency domain, the 256 spectral estimates are compressed into 32 logarithmically spaced frequency bands of constant fractional bandwidth (or equal "Q" filters). In the amplitude domain, the 12-bit data are logarithmically compressed to 7-bits plus sign using two alternate schemes: (a) a variable MSB truncation approach and (b) an algorithm based on the µ-Law commonly used in communication systems. The net result is a set of 32 full spectral matrices for the components and 32 spectral estimates for the field magnitude, transmitted to ground using 8-bit words but representing the original dynamic range of 12-bits. Further details of the FFT processor can be found in Acuña et. al. (1992) and Panetta et. al. (1992).

Finally, the DPU supports the distribution of high time resolution data to the NOAA Processor. A serial data stream consisting of zero corrected primary magnetometer data sampled at 30 samples per second plus ancillary range and miscellaneous information, is provided.

The nominal telemetry modes for ACE/MAG are illustrated in Table 2. Three modes are used:

1.	normal mode

2.	high rate mode

3.	enhanced mode.

Note that the different modes allocate different ratios of the available telemetry resources to the sampling of the Primary and Secondary magnetometers, the snapshot memory buffer and the FFT processor. Mode (1) is the default mode which provides equal sampling rates to the two magnetometers and will be used initially to characterize and evaluate the nature of the spacecraft generated magnetic field. Mode (2), the high rate mode which favors the Primary magnetometer is expected to be used during most of the mission. Mode (3) can be used to provide enhanced data for the Primary magnetometer at 6 vectors/second.

Table 2.

MAG Telemetry Modes

| Data Stream | Mode 1 | Mode 2 | Mode 3 |
| --- | --- | --- | --- |
| Primary Sensor | 108 bps (3) | 180 bps (5) | 216 bps (6) |
| Secondary Sensor | 108 bps (3) | 36 bps (1) | 0 |
| FFT | 32 bps | 32 bps | 32 bps |
| SSM | 48 bps | 48 bps | 48 bps |

The total bit rate is 304 bps in all modes.				()= Vectors/second

### 5 Power Converters and Thermal Control

The MAG instrumentation derives power from the 28 volt regulated spacecraft bus through two redundant power converters. Only one subsystem is powered at any particular time. The converters are high efficiency units which operate at 50 KHz and are synchronized to the master crystal clock of the DPU to minimize interference to other experiments onboard the spacecraft. Selection of the active converter is simply accomplished by powering the desired unit.

To maintain the fluxgate sensors within their optimum operating temperature range, it is necessary to provide heater power to the boom mounted triaxial sensor assemblies during periods of sun occultation. Since it is extremely difficult to reduce the stray magnetic field associated with the operation of D.C. powered foil heaters to acceptable levels for MAG, a magnetic amplifier operating at 50 KHz is used to obtain automatic, proportional control of AC power supplied to the heating elements. The nominal power required to maintain each sensors at the desired temperatures is estimated to lie in the range of 0.3 to 0.5 watts.

# 6 Management Plan

## 7 Approach

The ACE/MAG project will be managed at the University of Delaware - Bartol Research Institute with Norman F. Ness as Experiment Manager, Jacques L'Heureux as Instrument Manager, Charles W. Smith as Data Manager, and Debbie S. Booth as Administrative officer, all located in Sharp Lab on the main campus of the University of Delaware.

The MAG instrument is a modified MFI/WIND spare to be furnished and modified by the same NASA/GSFC team that designed and built the MFI. This hardware team will be led by Mario Acuña and the work will be carried out within Code 695 in the Laboratory for Extraterrestrial Physics (LEP). The key elements of their management approach is by conservative utilization of in-house capability, sharing of responsibilities according to expertise and experience, flexibility, modest use of out-of-house capability for fabrication, and constant surveillance through reviews. This approach has been used successfully by this team in the past to implement over 23 flight experiments, all accomplished within cost and on schedule.

The integration of MAG with ACE will be a team effort between BRI and GSFC to be led by BRI. Support for the ACE Science Center (ASC) will be the responsibility of the BRI. A Bartol Science Center (BSC) will be created for the processing and archiving of the MAG data and will be operated by BRI personnel.

The MO&DA Phase - which is not part of this proposal - will be a collaboration between the BRI team and a team at GSFC to be led by Dr. Len Burlaga of Code 692.

## 8 Organization

The organization chart for the ACE/MAG effort is shown in Figure 5.

## 9 Key Personnel

| Bartol Research Institute University of Delaware | · Norman F. Ness, President of the Bartol Research Institute and Experiment Manager for MAG. He has overall responsibility for the BRI subcontract and will be involved in the science, the instrumentation, the contract reporting, and the resource management. |
| --- | --- |
|  | · Jacques L'Heureux, Senior Research Scientist and Instrument Manager. He is responsible for the day-to-day implementation of the instrument development instrumentation which includes monitoring the progress of the work done at the GSFC. He will also be involved in contract reporting and resource management. |
|  | · Charles W. Smith, Senior Research Scientist and Data Processing Manager (DPM). Will assist the EM in establishing the detailed scientific objectives and the establishment of the data analysis requirements. Will also provide coordination with ASC and BSC personnel as necessary. |
|  | · Hua Tsao, Research Scientist and Programmer. Responsible to the DPM for the development and testing of mission-unique software and the integration and support of the BSC Workstation. |
|  | · Len Shulman, Electronics Engineer. Provide expertise in hardware implementation of GSE interfaces. |
|  | · Debbie S. Booth, Administrative Officer. Responsible to the EM for all procurement actions and financial bookkeeping activities. |
| NASA-Goddard Space Flight Center Greenbelt, MD | · Mario Acuña, Instrument Scientist at the Goddard Space Flight Center. for the Goddard supplied hardware. Has overall responsibility for the GSFC supplied hardware, the contract reporting, and the resource management. |
|  | · John Scheifele, Senior Engineer. Will act as Instrument Manager for the GSFC supplied hardware. Will supervise hardware redesign, fabrication and testing. |

## 10 Institutional Responsabilies

The institutional responsibilities are summarized in Table 3.

| Table 3. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Institutional Responsibilities |  |  |  |  |  |
| Activity | BRI | GSFC |  |  |
| 1. Project and Science Management |  |  |  |  |
| Program Management | X |  |  |  |
| Technical Management | X | x |  |  |
| Configuration Management | X | x |  |  |
| Planning and Scheduling | X | x |  |  |
| Project Support |  |  |  |  |
| Attend Project Meetings and Reviews | X | x |  |  |
| Document Generation | X |  |  |  |
| Activity | BRI | GSFC |  |  |
| Science Management | X |  |  |  |
| Financial Management | X | x |  |  |
| 2. System Engineering |  |  |  |  |
| System Engineering | x | X |  |  |
| Interface Management | x | X |  |  |
| 3. Performance Assurance |  |  |  |  |
| Quality Assurance | X | x |  |  |
| Reliability Studies | X | x |  |  |
| Safety Assurance | X | x |  |  |
| Contamination Studies | X |  |  |  |
| 4. Flight Hardware |  |  |  |  |
| Interface Rework |  | X |  |  |
| Firmware Re-Programming |  | X |  |  |
| Cabling to Sensors |  | X |  |  |
| 5. Analyses and Subsystem Tests |  |  |  |  |
| Structural Analysis |  | X |  |  |
| Thermal Analysis |  | X |  |  |
| Contamination Analysis |  | X |  |  |
| Vibration Testing | x | X |  |  |
| Thermal Vacuum Testing | x | X |  |  |
| EMI/EMC Testing | x | X |  |  |
| 6. Instrument GSE |  |  |  |  |
| Computer w/Display and Mass Storage |  | X |  |  |
| Interface to MAG |  | X |  |  |
| Generate and Test Software |  | X |  |  |
| Cabling to Sensors (2 sets) |  | X |  |  |
| 7. Integration and Test Support |  |  |  |  |
| Document Generation | X |  |  |  |
| Activity | BRI | GSFC |  |  |
| Integration and Tests Support | X | x |  |  |
| 8. Flight GSE for use in ASC and during Integration |  |  |  |  |
| Interface to S/C Simulator | X |  |  |  |
| Interface to ACE GSE & ASAAC | X |  |  |  |
| Generate and Test Software | X |  |  |  |
| 9. Bartol Science Analysis System |  |  |  |  |
| Purchase Workstation and Set-up System | X |  |  |  |
| Purchase Analysis Software | X |  |  |  |
| Mission Specific Software Development and Testing | X |  |  |  |
| 10. Launch Support and MO Planning |  |  |  |  |
| Provide Shipping and Storage Containers | X | X |  |  |
| Launch Support | X |  |  |  |
| Mission Operations Scheduling | X |  |  |  |
| Flight Operations Support | X |  |  |  |
| X= Lead Institution |  |  |  |  |

## 11 Work Breakdown Structure and WBS Dictionary

Our Work Breakdown Structure is shown on Figure 6. Following is a description of each of the WBS items.

### UD/BRI Direct Technical Labor (1.3.9.1)

Project Management (1.3.9.1.1):  Oversight and coordination of the overall scientific, technical and financial aspects of the MAG instrument effort.  Key supporting activities at the University of Delaware/Bartol Research Institute consists of:

·	Administrative management including the preparation of monthly 533 reports,

·	Scheduling of the coordinated MAG tasks among UD/BRI and the magnetometer experiment CoIs at the Goddard Space Flight Center, and

·	Reporting monthly on work progress by all groups along with the status of expenditures at UD/BRI.

System Engineering (1.3.9.1.2): Technical oversight and coordination of the entire MAG instrument refurbishment, calibration and adaptation efforts.  Included are:

·	Electrical and mechanical interface control,

·	Thermal analysis and design of the MAG instrument in coordination with the thermal modeling and supporting efforts of the ACE spacecraft project office at GSFC, and

·	The modeling of instrument performance as subsystem test results become available.

Following the onset of instrument-level testing, the trend of key performance parameters will be monitored. It should be noted that design of the MAG instrument interface adapter to the ACE spacecraft will be carried out by the Goddard Space Flight Center (GSFC). In addition, technical consultations and analyses by experts also at the GSFC are assumed to take place in the areas of thermal design and structural analysis.

Analyses & Subsystem Tests (1.3.9.1.3):  Included in this category are; a) the UD/BRI in-house checkout of magnetometer assemblies and subsystems, and b) coordination with Goddard and GSFC on MAG instrument structural and thermal analyses.

Ground Systems (1.3.9.1.4):  This activity is comprised of designing, fabricating and checking out one set of ground support for the inherited MAG instrument.  Also included in this category are the making of an instrument simulator, a spacecraft interface adapter simulator, special test equipment, calibration hardware, supporting ground test equipment and shipping, handling and storage equipment.

Performance Assurance (1.3.9.1.5):  This activity consists of supervising and carrying out provisions of the ACE payload Performance Assurance Implementation Plan (PAIP) as it applies to work conducted at, or under the direction of, the University of Delaware/Bartol Research Institute.  Conducting flight software inspections is an aspect of this activity.  Coordination with GSFC and NASA Goddard Space Flight Center Code 695.0  on the work being done there is included under this task as well.

Functional and Environmental Testing and Calibration (1.3.9.1.6):  Included are bench performance tests along with environmental tests and calibrations.  Environmental tests include thermal vacuum runs, EMC tests, vibration testing and acoustic testing all of which assumed to take place at the Goddard Space Flight Center.

Integration and Test Support (1.3.9.1.7):  This provides support for activities associated with integrating the MAG instrument onto the ACE spacecraft.  Short-Form test procedures and other documentation needed by the spacecraft integrator will be provided as well. Support is also provide for experiment operation during the more extensive spacecraft test sequences.

Science Support (1.3.9.1.8): The establishment of firm science requirements that fit within the available resources is an important aspect of this category.  Monitoring instrument performance throughout the instrument refurbishment and adaptation activities is also an important aspect.  Participation in science team meetings and splinter discussions on selected topics is also included.  Oversight of the instrument calibration activities and participation in key spacecraft system tests are part of this work category as well.

Launch Support and Early Operations Support (1.3.9.1.9):  Included are support for:

·	Launch site testing and

·	Experiment turn-on and checkout following injection into a transfer orbit to the L1 libration point.

Data Processing and Software Development (1.3.9.1.10):  Algorithm development and code generation for MAG instrument health and safety monitoring, quick-look data displays and scientific data processing are all part of this cost category.  Included as well is the support to be provided to Caltech for the development and checkout of the ACE Science Center along with a Remote Analysis Center at UD/BRI. This will include laying plans for, and testing readiness for, the Mission Operations and Data Analysis Phase.  Coordination of the MAG experiment Co-I requirements at GSFC is included under this activity as well.

### UD/BRI Materials, Supplies and Other Direct Charges (1.3.9.2)

Included in this category are expenses for office and laboratory supplies, materials and expendables used in support of the in-house MAG instrument activities.

(Note: It is not expected that any flight electronic parts or materials will be purchased by UD/BRI for adapting the MAG instrument to the ACE spacecraft.  The GSFC will be assigned that responsibility on behalf of the MAG team).

The category 'Other Direct Charges' includes telephone and fax charges, in-house graphic arts and reproduction charges as well as delivery charges.  Also  included  are engineering drafting charges, central computing charges, repair services for lab instruments, machine shop charges for rework or repair, and expenses for laboratory supplies, materials and expendables used in support of the in-house MAG performance verification, test and calibration efforts. Facility utilization charges associated with the in-house testing at UD/BRI are included in this category as well.

### UD/BRI Equipment Purchases (1.3.9.3)

Included are items costing more than $500 that have a manufacturer's model number or part number which serve a purpose to the ACE Project in their own right, or do so after incorporation into a higher level system.  Commercial laboratory equipment and computers that become part of ground support equipment (GSE) are included in this category.  So are desk top work stations as well as computers and peripherals for a remote analysis center of the distributed ACE payload ground data processing system.

### UD/BRI Travel (1.3.9.4)

Business-related transportation charges, lodging expenses and per diem for in-house personnel and/or consultants associated with ACE payload flight or ground system developments.

### UD/BRI Indirect Costs (1.3.9.5)

Indirect costs include:

·	administrative salaries, benefits and travel charges;

·	facilities operations and maintenance;

·	administrative computer equipment purchases, supplies and maintenance; and

·	basic telephone and FAX costs.

The overhead rates are reviewed at regular intervals and approved by an agency of the U.S. federal government.

### GSFC Code 692 and 695 Tasks (1.3.9.6)

Activities planned for the GSFC Code 692 and 695 Co-Investigator(s) include:

·	Design the necessary Interface (I/F) modifications to the WIND/MFI to adapt it to ACE;

·	Fabricate and test the I/F modifications

·	Provide assistance in calibrating the ACE/MAG instrument; and

·	Provide technical support for the MAG integration.

A separate budget for Code 692/695 participation is attached to this proposal. Actual funding will be done directly from the ACE Project to the LEP.

## 12 Contract Deliverables

The contract deliverables list will be derived from the list agreed on between Caltech and the GSFC Project Office. To be included are monthly and quarterly progress reports; monthly and quarterly financial reports (533M/Q); a final report; and any documentation and/or reports needed by Caltech to satisfy their deliverables list to the Project Office.

## 13 Key Assumptions

·	The spare MFI/WIND instrument must be available by the third quarter of 1994 to start I/F modifications.

## 14 Reviews and Reporting

Cost reporting to CIT will be done monthly and quarterly using forms 533M and 533Q respectively.

## 15 Cost Control

The financial statements include the assets, liabilities, fund balances, and financial activities of UD/BRI. To observe limitations and restrictions placed on the use of resources, the accounts of the Institute are maintained in accordance with fund accounting principles. Under this procedure, the receipts and resources and their related expenditure for specified uses are summarized in a separate group of accounts. Accordingly, the financial statements are presented by fund categories.

Fund balances restricted by outside sources may only be utilized with purposes established by the source of such funds and are in contrast with unrestricted funds over which the Board of Trustees retains full control to use in achieving any of its institutional purposes.

Revenue from grants and contracts is recognized as the work performed and includes recovery of indirect costs bases upon a proposed rate which is adjusted to actual upon audit by the contracting agency. Costs and expenses are charged to operations as incurred. Receipts from contracts and grants in excess of expenditures incurred are recorded as deferred income. Support revenue provided to the Institute from The Bartol Research Foundation is recognized on an accrual basis. All other revenue is reported as revenue when received in its respective funds.

Significant internal control structure policies and procedures used in administering federal award programs are listed as follows:

ACCOUNTING CONTROLS

·	Revenues/receipts

·	Purchases/disbursements

·	Payroll

·	External financial reporting

GENERAL REQUIREMENTS

·	Political Activity

·	Davis-Bacon Act

·	Civil Rights

·	Cash Management

·	Federal financial reports

·	Allowable cost/cost principles

·	Drug-free Workplace Act

·	Administrative requirements

SPECIFIC REQUIREMENTS

·	Types of services

·	Eligibility

·	Matching, level of effort of earmarking

·	Reporting

·	Cost allocation

·	Special program requirements for research and development

·	Monitoring sub-recipients

## 16 Contract Management

Awards include all grants, contracts, and similar agreements entered into directly between the Bartol Research Institute and agencies and departments of the federal government and all sub-awards to the Institute by non-federal organizations pursuant to federal grants, contracts and similar agreements. The awards are classified into major program and non-major programs categories in accordance with the provisions of Office of Management and Budget (OMB) Circular A-133, Audits of Institutions of Higher Education and Other Nonprofit Institutions. The full names of the sponsoring agencies include:

·	NSF - National Science Foundation

·	DOE - Department of Energy

·	NASA - National Aeronautics and Space Administration

The management of the Institute is responsible for establishing and maintaining an internal control structure. In fulfilling this responsibility, estimates and judgments by management are required to assess the expected benefits and related cost of internal control structure policies and procedures. The objectives of internal control structure are to provide management with reasonable assurance that assets are safe-guarded against loss from unauthorized use or disposition, and that transactions are executed in accordance with management's generally accepted accounting principles.

Report of compliance is issued by KPMG Peat Marwick, Certified Public Accounts.

# 17 Development Plan

## 18 Instrument Heritage

The ACE/MAG instrument will be a modification of the spare MFI instrument built for the WIND mission with the prime unit being scheduled to be launched in 1994. The fluxgate sensors used in that instrument are the latest in a series developed for weak magnetic field measurements by Acuña et. al. (1974) and which have been extensively used in missions like VOYAGER, AMPTE, GIOTTO, Mars Observer, CLUSTER, etc. due to their superior performance and low power consumption.

## 19 Changes/Additions from Heritage

The ACE/MAG instrument will be a slightly modified MFI with all the changes being in the I/O section and to the on-board firmware to adapt to the ACE telemetry scheme.

## 20 Development

### 21 New Developments Hardware Tasks

No new development hardware tasks have been identified.

### 22 Software Development

On-board Software: The on-board firmware that currently exists in the MFI/WIND spare unit will be modified to adapt the instrument to the ACE telemetry scheme. This effort will be done at the GSFC by LEP personnel already familiar with the instrument.

GSE-Software: The GSE software for ACE/MAG will be a modification of software written for the MFI/WIND instrument with only the input section needing significant modifications.

### 23 GSE Usage

The GSE for ACE/MAG consist of IBM-PCs with a specially designed interface card for interfacing with the instrument. This GSE will travel with the instrument during environmental testing and integration. A more powerful version of the GSE will be at the POCC for quick-look data display and analysis.

### 24 Key Decision Points

None.

### 25 Part Buy Lead Times

No advanced purchase of parts will be required.

### 26 Key Facilities

The modifications to the MFI instrument are to be done at the LEP of the GSFC by members of the original MFI/WIND team. Several test facilities at the GSFC will be required to satisfy the test requirements of ACE/MAG. These tests are summarized in the test matrix.

## 27 Work Flow Diagram and Schedule

The Work flow for ACE/MAG is rather simple and straightforward and the work flow has been combined with the schedule as shown in Figure 7-1/2.

## 28 Calibration

### 29 Methodology and Requirements

It will be necessary to calibrate both magnetometers in the magnetic coil at the GSFC Magnetic Test Facility before the start of the sequence of environmental testing as well as after completion to verify integrity of the instrumentation.

We have requested that the magnetic field of the S/C be less than 0.1 nT at the position of the sensors. The best way to verify this requirement is for the project to permit magnetic mapping of the entire powered-up S/C during post integration S/C Systems testing at the GSFC Magnetic Test Facility, as has been done for all previously GSFC managed S/C. We strongly urge that this be done in the ACE mission also.

## 30 Test and Integration

### 31 Instrument Test Matrix w/Facilities Requirements

The tests and the location where they will be performed are listed in Table 4.

Table 4.

Instrument Test Matrix

| Test | Location |
| --- | --- |
| Primary Structure Structural Analysis | GSFC Facility |
| Primary Structure Composite Tests | GSFC Facility |
| Interface FMEA's | GSFC Facility |
| Electronic Parts Stress Analysis | GSFC Facility |
| Thermal Analysis | GSFC Facility |
| Center of Gravity | GSFC Facility |
| Moments of Inertia | GSFC Facility |
| Test | Location |
| Pressure Profile | GSFC Facility |
| Vibration | GSFC Facility |
| EMC | GSFC Facility |
| Thermal-Vacuum | GSFC Facility |
| Calibration Facility Support | GSFC Facility |

### 32 Test and Integration Flow

Testing time has been identified on our schedule (Figure 7). A calibration at the GSFC magnetic Testing Facility will be schedule prior to the start of all the environment tests as well as after.

### 33 Constraints

None identified.

## 34 Product Assurance

The Caltech PAIP as modified by the appendix relating to BRI will be followed. The Instrument Manager will act as QA Manager.

Our hardware collaborators at GSFC are on the other hand negotiating their own PAIP with the ACE Project office. At GSFC, a Quality Assurance and Safety Engineer will be responsible to the Goddard Instrument Manager for insuring that the experimental parts, materials, design and safety margins conform to the project requirements for quality assurance, reliability and safety.

## 35 Configuration Control

The MAG Experiment Manager is responsible for overall control, evaluation and approval of all configuration changes affecting flight hardware, software, interfaces, ground data processing equipment (GSE) and documentation for the ACE/MAG instrument. Day-to-day implementation and coordination of the Configuration Management (CM) procedures will be carried out by the MAG Instrument Manager (IM), and will be authorized to represent the PI in all CM related activities and negotiations. He will be the experiment point-of-contact for matters related to Configuration Control.

The IM will be responsible for any changes affecting interfaces, costs, or scheduling. Changes with only internal impact (not affecting interfaces, cost, or scheduling) will be reviewed with and approved by the MAG EM. The IM will then submit a configuration change request for any proposed changes to baselined documentation.

The MAG IM will be responsible to CIT for providing detailed as-built configuration records as the instrument proceeds through modification, integration, and testing.

# 36 Operations Plan

## 37 Instrument Commanding

The MAG experiment possesses 3 modes of operation that divide the allocated telemetry differently between the two magnetometer data streams, the FFT, and the Snapshot buffers. Ground-station initiated and stored commands are required to change modes of operation between the preprogrammed states. The default executive and processing program is stored in Read-Only-Memory (ROM) and no subsequent commands or memory loads are required after initial turn-on. The processor can be reprogrammed in-flight, but uplink telemetry allocations will necessitate multiple passes for each complete reprogramming. Uplinking of six new offset values will be required periodically (approximately monthly). Calibrations, alignments, and other parameters may also be updated occasionally. Switching between processors A and B will also be commanded through occasional telemetry uplinks.

## 38 Data Analysis

### 39 Data Flow

The POCC will provide only minimal health monitoring and occasional uplinks for MAG due to the robust, pre-programmed nature of the instrument. MAG does not possess states or command sequences which are threatening to the instrument and same-pass uplinks in response to monitoring of health parameters are not required. Health parameters will be located within each major frame and monitoring of these parameters by the POCC will provide the earliest warning of instrument malfunctions necessary for rapid restoration of data quality.

### 40 Level 0, Level 1 and Level 2 Processing

A major consideration in the design of the MAG software and operating modes is the general requirement by the ACE Mission for each investigation to produce high-level data at the ASC for consultation by the other instrument teams without the continuous intervention of the MAG investigators. For this reason, and since the ASC will be sent the full MAG data set in duplication of what is sent to BRI/UD, we have decided to provide both locations with duplicates of the data analysis software and parameter files (offsets, alignments, etc.). Intermediate-level data products, such as time series of intermediate- and low-time resolution magnetic field measurements in heliographic coordinates, will be routinely generated at the ASC for use by the other investigators and for archival purposes. In addition, analysis routines will be provided to produce high-level data products, such as spectra, in a convenient and interactive manner. We believe that the production of high-level data products by appropriate investigators is more useful than the routine generation of these products by automated packages. High-level data products produced by the investigators will be stored at the ASC for consultation.

We now briefly describe the phases of the processing program to reside at both the ASC and BRI/UD BSC (Bartol Science Center). The ASC will receive ACE data from DSN daily while the BSC will receive data on DAT tapes at a previously agreed upon rate. The deblocking of data at BRI/UD is performed with a program specifically designed to strip the requested files from the delivery medium and place them on computer hard disk. The tapes will be retained for archival purposes. At this stage, the files contain MAG measurements in their raw, uncalibrated form. Further processing is performed to create a Level 0 "Standard Format File" containing magnetic field and orbit/attitude data. Level 1 data is obtained by processing the Standard Format File, correcting to physical units using calibration data, correcting for alignment, offsets, etc. and despinning to an inertial reference frame. Level 2 data is obtained by processing Level 1 data to obtain appropriate time resolutions in physical coordinates (such as heliographic). Additional, high-time resolution, Level 2 data is obtained by examination and storage in the database of the FFT and Snapshot buffer contents. Electronic drift and sensor misalignment values will also be part of Level 2 data.

### 41 Science Operations Center Interface

Since analysis software will be duplicated in the ASC and BRI/UD BSC facilities for processing to all levels, routine transmission between the ASC and BRI/UD is expected to involve relatively small parameter files with only occasional transmission of new software. Data will not be routinely transmitted. However, logins to the ASC for interactive data analysis and reduction sessions may be required on a daily basis. Either a simple NSI or Internet connection will suffice. BRI/UD currently supports both. Occasionally, it may be desirable to write either a magnetic tape, magneto-optical, or CD-ROM disk at the ASC for shipment to BRI/UD or other site, at times in response to requests for data from non-ACE investigators. This capability at the ASC is desirable.

## 42 Operational Facilities

Since BRI/UD will retain the full MAG data set, we anticipate local storage of Level 0, 1, and 2 data on magneto-optical disks with backup to DAT tapes. The BRI/UD BSC will retain the "master library" of analysis routines from which the ASC library will be maintained. A networked graphics workstation will be purchased for the routine reduction and analysis of ACE MAG data. Subject to possible change, the present configuration of this workstation and peripherals is: a DEC 3000/400 OpenVMS Workstation, dual optical storage unit (1 GByte each); a 4GByte 4mm DAT tape drive and an Uninterruptible Power Supply. This support hardware will be attached to the BRI/UD computing network to facilitate access to additional, BRI-supported peripheral hardware and software, such as printers, network gateways, and commercial graphics packages. An appropriate visualization software package will be purchased.

References

Acuña, M.H., IEEE Tans. Magnetics, MAG-10, 519, 1974

Acuña, M.H., N.F. Ness, Jupiter, T. Gehrels (ed.), Univ. of Arizona Press, Tucson, 830, 1976a.

Acuña, M.H. and N.F. Ness, JGR, 81, 2917, 1976b.

Burlaga, L.F., K.W. Behannon, and L. W. Klein, Compound streams, magnetic clouds, and major geomagnetic storms, JGR, 92, 5725, 1987.

Farrell, W.M., A method for calibrating a magnetometer onboard a spinning spacecraft, NASA/LEP Technical Memo, 1992.

Kokubun, S., et. al., GEOTAIL Interim Report, Institute of Space and Astronautical Science, p. 55, November 1990.

Mish, W.H. and R.P. Lepping, Magnetic field experiment data processing systems: Explorers 47 and 50, NASA/GSFC X-694-76-158, August 1976.

Moldwin M., and W. J. Hughes, The evolution of plasmoids: Survey of ISEE 3 GEOTAIL data, EOS, Transactions AGU, p.242, (SME32E-3), April 23, 1991.

Moldwin, Mark B., and W.J. Hughes Multi-Satellite Observations of Plasmoids: IMP 8 and ISEE 3, GRL, 19, No 11, 1081, 1992.

Ness, N.F., Magnetometers for space research, Space Sci. Rev., 11, 111-222, 1970.

Ness, N.F., K.W. Behannon, R.P. Lepping, and K.H. Schatten, Use of two magnetometers for magnetic field measurements on a spacecraft, JGR, 76, 3564, 1971.

Panetta, P.V. and M.H. Acuña, WIND MFI FFT Processor Requirements Document, Rev. 10, Aug. 9, 1991.

Panetta, P.V., WIND MFI Telemetry Bits Definition Document, Rev. 1, Feb. 25, 1992.

Panetta, P.V., WIND MFI Flight Software Description Document, Rev. 2, March 16, 1992.

Richardson, I.G., et. al., Plasmoid-associated energetic ion bursts in the deep geomagnetic tail: Properties of plasmoids and the post-plasmoid plasma sheet, JGR, 92, 9997, 1987.

Slavin, J.A., R.P. Lepping, and D.N. Baker, IMP-8 observations of traveling compression regions: New evidence for near-earth plasmoids and neutral lines, GRL, 17, 913, 1990.

A Proposal Submitted to

The California Institute of Technology

Pasadena, CA 91125

Att: Dr. Edward C. Stone

in Reference to the

Advanced Composition Explorer (ACE)

Phase C/D RFP

for the

Magnetometer Instrument (MAG)

Section B

Cost Plan

Submitted by the

Bartol Research Institute

University of Delaware

Newark, DE 19716

Norman F. Ness

Experiment Manager and

President of the Bartol Research Institute

June 1993

Section B

Table of Contents

Costs Estimates for the BRI and GSFC Collaboration

1.	Summary Costs for the Collaboration (Exhibit 3A).

2.	Plots of Funding Profile, and distribution between BRI and GSFC.

3.	Summary Costs for the Collaboration with the Escalation rates set at 0%(Exhibit 3A)

Costs Estimates for the Bartol Research Institute

1.	Summary Costs for the Bartol Research Institute (Exhibit 3A)

2.	Rate Summary (Schedule J)

3.	Summary of Hours (Schedule A)

4.	Summary of Direct Labor Hours (Schedule B)

5.	Materials and Services and Other Direct Costs (Schedule F)

6.	Travel Costs (Schedule G)

7.	Equipment Costs (Schedule I-1)

8.	Summary Costs for the Bartol Research Institute with the labor and Other Escalation rates set at 0%(Exhibit 3A)

Costs Estimates for the Goddard Space Flight Center

1.	Summary Costs for the Goddard Space Flight Center (Exhibit 3A)

2.	Rate Summary (Schedule J)

3.	Summary of Hours (Schedule A)

4.	Summary of Direct Labor Hours (Schedule B)

5.	Materials and Services and Other Direct Costs (Schedule F)

6.	Summary Costs for the Goddard Space Flight Center with the Escalation rates set at 0%(Exhibit 3A)

Section B

Appendices

Appendix A.	Form 1411

Appendix B.	Small Business Subcontracting Plan

Appendix C.	Copy of Government Approved Benefits and Indirect Costs Rates

Appendix D.	Copy of Most Recent A-128/133 Audit Report

Appendix E.	Backup support for Salaries

Appendix F.	Backup Support for Equipment and Major Items Purchases

Appendix G.	Completed Lobbying Certificate

Appendix H.	Completed Procurement Integrity Certification

Appendix I.	Other Form from Reps and Cert. Sections

1. Cost Schedules

1.1 Bartol Research Institute

The Cost estimates for the Bartol Research Institute are based on the following facts:

·	The base salaries are those in effect in June of 1993 with the support documentation in Appendix E.

·	Our latest Fringe Benefits and Overhead Rates audit dated March 1, 1993 can be found in Appendix C. The report from the most recent audit is due in the fall of 1993.

·	The inflation rates applied are from the NASA Inflation Index Table dated April 12, 1993.

·	The Logging and M&IE rates are from the table titled "New Travel Reimbursement Rates" as posted on the NASA Travel Bulletin Board on NASAMAIL on March 22,1993. The airfares used are those quoted to us for unrestricted coach fares.

1.2 Goddard Space Flight Center

The Cost estimates for the Goddard Space Flight Center are based on the following facts:

·	Civil service labor is free of charge except for the MPS charge estimated at $26K/MY. No inflation was applied to this rate.

·	LEP Tax rate was assumed to be 6%.

Summary of Costs Estimates for

the BRI and GSFC Collaboration

Costs Estimates for

the Bartol Research Institute

Costs Estimates for

the Goddard Space Flight Center

Appendix A.

Form 1411

Appendix B.

Small Business Subcontracting Plan

To be supplied at a later date.

Appendix C.

Copy of Government Approved Benefits and Indirect Costs Rates

Appendix D.

Copy of Most Recent A-128/133 Audit Report

Appendix E.

Backup support for Salaries

Appendix F.

Backup Support for Equipment and Major Items Purchases

Appendix G.

Completed Lobbying Certificate

Appendix H.

Completed Procurement Integrity Certification

Appendix I.

Other Form from Reps and Cert. Sections